## 21 - 28 Feb 26
|  |  |  | Dinesh | Dinesh | MIYARAM | MIYARAM | NO EDIT | MIYARAM | NIRBHAY | NIRBHAY | NIRBHAY | NO EDIT | NIRBHAY | MIYARAM | MIYARAM | NO EDIT | MIYARAM JI | MIYARAM | ISTYAAR | ISTYAAR | NO EDIT | ISTYAAR | Rajan | Rajan | NO EDIT | GAGAN JI | GAGAN | GAGAN | NO EDIT | GAGAN | Rajan | SHIV KUMAR | SHIV KUMAR | NO EDIT |  | Dinesh
S NO. | STYLE NO. | COLOUR | ITEM | ORDER QTY | ITEM WISE QTY | TODAY CUTING QTY | TOTAL QTY | BALANCE QTY | CUTTING REMARK | ISSUE EMB | TODAY INHOUSE EMB QTY | TOTAL QTY | BALANCE QTY | EMB REMARK | TODAY RE CUTTING EMB | TOTAL RECUTTING | BALANCE EMB RECUTTING | REMARK RECUTTING | Issue Stiching | TODAY STITCHING QTY | TOTAL QTY | BALANCE QTY | REMARK STITCHING | WIP TODAY QTY | TOTAL QTY | BALANCE QTY | ISSUE ADDA WORK | TODAY ADDA QTY | TOTAL QTY | BALANCE QTY | REMARK ADDA WORK | ISSUE FINISHING QTY | TODAY FINISHING QTY | PACK TOTAL QTY | CUTTING TO FINISHING BALANCE QTY | ISSUE TO FINISHING BALANCE | REMARK | Timeline
| Total - |  |  | 21036 | 59292 | 0 | 56684 | -608 | 0 | 34960 | 0 | 33362 |  |  | 0 | 35475 | -1491 | 0 | 42517 | 0 | 40285 | -16399 |  | 0 | 39875 | -1806 | 12165 | 19 | 10396 | #VALUE! |  | 37962 | 1311 | 32953 | -9564 | -5009
1 | YDPL-3512 | MUSTARD | KURTA | 724 | 724 | 0 | 724 | 0 | ok | 724 | 0 | 724 | 0 | OK | 0 | 724 | 0 | OK | 724 | 0 | 717 | -7 | 7 pcs emb nahi h | 0 | 709 | -8 | 709 | 0 | 709 | 0 | ok | 709 | 0 | 684 | -40 | -25 | IN FINISHING Part change | 2026-03-08
|  |  | BOTTOM |  | 724 | 0 | 724 | 0 | ok | 0 | 0 | 0 | 0 | OK | 0 | 724 | 0 | OK | 724 | 0 | 724 | 0 | ok | 0 | 724 | 0 | 0 | 0 | 0 | 0 | ok | 709 | 0 | 684 | -40 | -25 | IN FINISHING
|  |  | DUPATTA |  | 724 | 0 | 724 | 0 | 12 dp on die | 724 | 0 | 724 | 0 | OK | 0 | 724 | 0 | OK | 724 | 0 | 724 | 0 | ok | 0 | 724 | 0 | 0 | 0 | 0 | 0 | ok | 709 | 0 | 684 | -40 | -25 | 30 duppate pending | 2026-03-08
|  | PURPLE | KURTA | 692 | 692 | 0 | 692 | 0 | ok | 692 | 0 | 692 | 0 | OK | 0 | 692 | 0 | OK | 692 | 0 | 672 | -20 | 20 pcs emb pending | 0 | 672 | 0 | 672 | 0 | 672 | 0 | OK | 692 | 0 | 684 | -8 | -8 | IN FINISHING | 2026-03-08
|  |  | BOTTOM |  | 692 | 0 | 692 | 0 | ok | 0 | 0 | 0 | 0 | OK | 0 | 692 | 0 | OK | 692 | 0 | 692 | 0 | OK | 0 | 692 | 0 | 0 | 0 | 0 | 0 | OK | 692 | 0 | 684 | -8 | -8 | IN FINISHING
|  |  | DUPATTA |  | 692 | 0 | 692 | 0 | ok | 692 | 0 | 692 | 0 | OK | 0 | 692 | 0 | OK | 692 | 0 | 692 | 0 | OK | 0 | 717 | 25 | 0 | 0 | 0 | 0 | OK | 692 | 0 | 684 | -8 | -8 | IN FINISHING
2 | YDPL-3467 | BLUE | KURTA | 556 | 556 | 0 | 556 | 0 | ok | 556 | 0 | 556 | 0 | OK | 0 | 556 | 0 | OK | 556 | 0 | 554 | -2 | REJECT | 0 | 551 | -3 | 551 | 0 | 551 | 0 | OK | 551 | 0 | 540 | -16 | -11 | Finishing | 2026-03-07
|  |  | BOTTOM |  | 556 | 0 | 556 | 0 | ok | 0 | 0 | 0 | 0 | OK | 0 | 556 | 0 | OK | 556 | 0 | 556 | 0 | OK | 0 | 556 | 0 | 0 | 0 | 0 | 0 |  | 556 | 0 | 540 | -16 | -16 | Finishing
|  |  | DUPATTA |  | 556 | 0 | 556 | 0 | ok | 556 | 0 | 556 | 0 | OK | 0 | 556 | 0 | OK | 556 | 0 | 556 | 0 | CUTTING PENDING | 0 | 559 | 3 | 0 | 0 | 0 | 0 |  | 540 | 0 | 540 | -16 | 0 | Finishing
|  | MUSTARD | KURTA | 492 | 492 | 0 | 492 | 0 | OK | 492 | 0 | 492 | 0 | OK | 0 | 492 | 0 | OK | 492 | 0 | 487 | -5 | REJECT | 0 | 485 | -2 | 486 | 0 | 486 | 0 | OK | 485 | 0 | 440 | -52 | -45 | IN FINISHING 26/02 | 2026-03-07
|  |  | BOTTOM |  | 492 | 0 | 492 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 492 | 0 | OK | 492 | 0 | 492 | 0 | OK | 0 | 492 | 0 | 0 | 0 | 0 | 0 |  | 492 | 0 | 440 | -52 | -52 | IN FINISHING
|  |  | DUPATTA |  | 492 | 0 | 492 | 0 | OK | 492 | 0 | 492 | 0 | OK | 0 | 492 | 0 | OK | 492 | 0 | 500 | 8 | OK | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  | 500 | 0 | 440 | -52 | -60 | IN FINISHING
3 | YDPL-3491 | CREAM | KURTA | 580 | 580 | 0 | 580 | 0 | OK | 580 | 0 | 580 | 0 | OK | 0 | 580 | 0 | OK | 580 | 0 | 579 | -1 | REJECT | 0 | 578 | -1 | 578 | 0 | 578 | 0 | OK | 578 | 0 | 544 | -36 | -34 | IN FINISHING | 2026-03-09 |  | 2026-03-06
|  |  | BOTTOM |  | 580 | 0 | 580 | 0 | IN | 0 | 0 | 0 | 0 | OK | 0 | 580 | 0 | OK | 568 | 0 | 568 | -12 | OK | 0 | 568 | 0 | 0 | 0 | 0 | 0 |  | 568 | 0 | 544 | -24 | -24 | IN FINISHING / 12 pant in sttiching
|  |  | DUPATTA |  | 580 | 0 | 580 | 0 | OK |  | 0 | 0 | 0 | OK | 0 | 560 | 0 | SHORT FABRIC | 0 | 0 | 560 | -20 | OK | 0 | 560 | 0 | 0 | 0 | 0 | 0 |  | 560 | 0 | 544 | 544 | -16 | IN Finishing
4 | YDPL-3513 | GREEN | KURTA | 612 | 612 | 0 | 612 | 0 | OK | 612 | 0 | 584 | -28 | 2026-02-28 | 0 | 556 | -28 | ON EMB | 612 | 0 | 596 | -16 | CUTTING PENDING | 0 | 596 | 0 | 596 | 0 | 597 | 1 |  | 596 | 0 | 547 | -65 | -49 | Fini & SLEEVE 16PCS KALI 28PCS EMB WORK (KTPL) | 2026-03-09
|  |  | BOTTOM |  | 612 | 0 | 612 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 556 | 556 | OK | 612 | 0 | 612 | 0 | OK | 0 | 612 | 0 | 0 | 0 | 0 | 0 |  | 600 | 0 | 547 | -65 | -53 | IN FINISHING 26/02 | Delayed
|  |  | DUPATTA |  | 612 | 0 | 612 | 0 | OK | 612 | 0 | 612 | 0 | OK | 0 | 612 | 0 | OK | 612 | 0 | 645 | 33 | OK | 0 | 645 | 0 | 0 | 0 | 0 | 0 |  | 600 | 0 | 547 | -65 | -53 | IN FINISHING
|  | PURPLE | KURTA | 616 | 616 | 0 | 616 | 0 | OK | 616 | 0 | 596 | -20 | 2026-02-28 | 0 | 576 | -20 | ON EMB | 616 | 0 | 590 | -26 | CUTTING PENDING | 0 | 588 | -2 | 589 | 0 | 588 | -1 |  | 588 | 0 | 534 | -82 | -54 | SLEEVE 16PCS KALI 20 PCS EMB WORK (KTPL) | 2026-03-09
|  |  | BOTTOM |  | 616 | 0 | 616 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 616 | 616 | OK | 616 | 0 | 616 | 0 | OK | 0 | 616 | 0 | 0 | 0 | 0 | 0 |  | 616 | 0 | 534 | -82 | -82 | IN FINISHING
|  |  | DUPATTA |  | 616 | 0 | 616 | 0 | OK | 616 | 0 | 616 | 0 | OK | 0 | 616 | 0 | OK | 616 | 0 | 607 | -9 | CUTTING SIDE PENDING | 0 | 607 | 0 | 0 | 0 | 0 | 0 |  | 607 | 0 | 534 | -82 | -73 | IN FINISHING
5 | YDPL-3496 | OFF WHITE | SHIRT | 540 | 540 | 0 | 540 | 0 | OK | 560 | 0 | 540 | -20 | OK | 0 | 540 | 0 |  | 540 | 0 | 540 | 0 |  | 0 | 509 | -31 | 509 |  | 509 | 0 |  | 509 | 0 | 372 | -168 | -137 | IN FINISHING | 2026-03-10
|  |  | BOTTOM |  | 540 | 0 | 540 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 540 | 540 |  | 540 | 0 | 540 | 0 |  | 0 | 540 | 0 | 0 | 0 | 0 | 0 |  | 540 | 0 | 372 | -168 | -168 | IN FINISHING
6 | YDPL-3492 | BLUE | KURTA | 532 | 532 | 0 | 532 | 0 | OK | 532 | 0 | 532 | 0 | OK | 0 | 532 | 0 |  | 532 | 0 | 528 | -4 | ON MACHINE | 0 | 528 | 0 | 0 | 0 | 0 | 0 |  | 528 | 0 | 512 | -20 | -16 | IN FINISHING | 2026-03-07
|  |  | BOTTOM |  | 532 | 0 | 532 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  | 532 | 0 | 532 | 0 | ON MACHINE | 0 | 532 | 0 | 0 | 0 | 0 | 0 |  | 532 | 0 | 512 | -20 | -20 | IN FINISHING |  |  | 2026-03-06
|  |  | DUPATTA |  | 532 | 0 | 532 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 532 | 532 |  | 478 | 0 | 532 | 0 | CUTTING PENDING | 0 | 532 | 0 | 0 | 0 | 0 | 0 |  | 532 | 0 | 512 | 34 | -20 | InHouse
|  | WINE | KURTA | 500 | 500 | 0 | 500 | 0 |  | 500 | 0 | 492 | -8 | 2026-12-28 | 0 | 484 | -8 |  | 492 | 0 | 493 | -7 | ON MACHINE | 0 | 493 | 0 | 0 | 0 | 0 | 0 |  | 493 | 0 | 476 | -16 | -17 | Sttiching & 7 Front Pending emb 26/02 Debit emb | 2026-03-07
|  |  | BOTTOM |  | 500 | 0 | 500 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  | 500 | 0 | 500 | 0 | CUTTING PENDING | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  | 528 | 0 | 476 | -24 | -52 | In Sttiching
|  |  | DUPATTA |  | 500 | 0 | 500 | 0 | OK | 500 | 0 | 500 | 0 | OK | 0 | 500 | 0 |  | 441 | 0 | 500 | 0 | CUTTING PENDING | 0 | 500 | 0 | 0 | 0 | 0 | 0 |  | 441 | 0 | 476 | 35 | 35 | Inhouse
7 | YDPL-3478 | WHITE | KURTA | 600 | 600 | 0 | 600 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  | 600 | 0 | 598 | -2 | ON MACHINE | 0 | 598 | 0 | 0 | 0 | 0 | 0 |  | 598 | 0 | 560 | -40 | -38 | IN FINISHING | 2026-03-08 |  | 2026-03-06
|  |  | BOTTOM |  | 600 | 0 | 600 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 |  | 0 |  | 600 | 0 | 600 | 0 | CUTTING PENDING | 0 | 600 | 0 | 0 | 0 | 0 | 0 |  | 600 | 0 | 560 | -40 | -40 | IN FINISHING
|  |  | DUPATTA |  | 600 | 0 | 600 | 0 | OK | 600 | 0 | 600 | 0 | OK | 0 | 600 | 0 |  | 600 | 0 | 570 | -30 | ON MACHINE | 0 | 570 | 0 | 0 | 0 | 0 | 0 |  | 570 | 0 | 560 | -40 | -10 | 30 duppate pending & IN FINISHING | 2026-03-08
|  | PEACH | KURTA | 604 | 604 | 0 | 604 | 0 | OK | 604 | 0 | 604 | 0 | OK | 0 | 604 | 0 |  | 604 | 0 | 602 | -2 | ON MACHINE | 0 | 602 | 0 | 0 | 0 | 0 | 0 |  | 583 | 0 | 560 | -44 | -23 | IN FINISHING | 2026-03-08
|  |  | BOTTOM |  | 604 | 0 | 604 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  | 604 | 0 | 599 | -5 | KASHIF | 0 | 599 | 0 | 0 | 0 | 0 | 0 |  | 599 | 0 | 560 | -44 | -39 | IN FINISHING
|  |  | DUPATTA |  | 604 | 0 | 604 | 0 | OK | 604 | 0 | 604 | 0 | OK | 0 | 604 | 0 |  | 604 | 0 | 578 | -26 | CUTTING PENDING | 0 | 578 | 0 | 0 | 0 | 0 | 0 |  | 578 | 0 | 560 | -44 | -18 | 26 Duppate pending & IN FINISHING | 2026-03-08
8 | ADPL-3433R1 | BLUE | KURTA | 420 | 420 | 0 | 420 | 0 | OK | 420 | 0 | 420 | 0 | OK | 0 | 420 | 0 |  | 420 | 0 | 411 | -9 | KASHIF | 0 | 411 | 0 | 411 |  | 411 | 0 |  | 411 | 237 | 368 | -52 | -43 | IN FINISHING | 2026-03-07
|  |  | BOTTOM |  | 420 | 0 | 420 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  | 420 | 0 | 420 | 0 |  | 0 | 420 | 0 | 0 | 0 | 0 | 0 |  | 420 | 237 | 368 | -52 | -52 | IN FINISHING
|  |  | DUPATTA |  | 420 | 0 | 420 | 0 | OK | 420 | 0 | 420 | 0 | OK | 0 | 420 | 0 |  | 420 | 0 | 420 | 0 |  | 0 | 420 | 0 | 0 | 0 | 0 | 0 |  | 420 | 237 | 368 | -52 | -52 | IN FINISHING
|  | MAHROON | KURTA | 420 | 420 | 0 | 420 | 0 | OK | 420 | 0 | 420 | 0 | OK | 0 | 420 | 0 |  | 420 | 0 | 403 | -17 | ON MACHINE | 0 | 402 | -1 | 402 |  | 402 | 0 |  | 402 | 200 | 396 | -24 | -6 | IN FINISHING | 2026-03-08
|  |  | BOTTOM |  | 420 | 0 | 420 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  | 420 | 0 | 420 | 0 |  | 0 | 420 | 0 | 0 | 0 | 0 | 0 |  | 420 | 200 | 396 | -24 | -24 | IN FINISHING
|  |  | DUPATTA |  | 420 | 0 | 420 | 0 | OK | 420 | 0 | 420 | 0 | OK | 0 | 420 | 0 |  | 420 | 0 | 420 | 0 |  | 0 | 420 | 0 | 0 | 0 | 0 | 0 |  | 420 | 200 | 396 | -24 | -24 | IN FINISHING
9 | ADPL-3484 | GREEN | KURTA | 376 | 376 | 0 | 376 | 0 | OK | 376 | 0 | 376 | 0 | OK | 0 |  | -376 |  |  | 0 | 0 | -376 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | HAND CUTTING | 2026-03-01 | 2026-03-10 | 2026-03-13
|  |  | BOTTOM |  | 376 | 0 | 376 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 |  | 0 |  | 376 | 0 | 0 | -376 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -376 | 0 | WIP
|  |  | DUPATTA |  | 376 | 0 | 376 | 0 | OK | 376 | 0 | 376 | 0 | OK | 0 | 376 | 0 |  | 376 | 0 | 0 | -376 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -376 | 0 | WIP
|  | PURPLE | KURTA | 372 | 372 | 0 | 372 | 0 | OK | 372 | 0 | 372 | 0 | OK | 0 |  | -372 |  |  | 0 | 0 | -372 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | HAND CUTTING | 2026-03-01 | 2026-03-10 | 2026-03-13
|  |  | BOTTOM |  | 372 | 0 | 372 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 |  | 0 |  | 372 | 0 | 376 | 4 | EXTRA CUTTING | 0 | 376 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -372 | 0 | WIP
|  |  | DUPATTA |  | 372 | 0 | 372 | 0 | OK | 372 | 0 | 372 | 0 | OK | 0 | 372 | 0 |  | 372 | 0 | 0 | -372 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -372 | 0 | WIP
10 | YDPL-3463 | BLUE | KURTA | 456 | 456 | 0 | 456 | 0 | OK | 456 | 0 | 456 | 0 | OK | 0 | 456 | 0 |  | 456 | 0 | 455 | -1 | sonu | 0 | 455 | 0 | 455 |  | 455 | 0 |  | 455 | 0 | 400 | -56 | -55 | IN Finishing | 2026-03-07
|  |  | BOTTOM |  | 456 | 0 | 456 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 |  | 0 |  | 456 | 0 | 436 | -20 | ON MACHINE | 0 | 436 | 0 | 0 | 0 | 0 | 0 |  | 455 | 0 | 400 | -56 | -55 | IN Finishing
|  |  | DUPATTA |  | 456 | 0 | 456 | 0 | OK | 456 | 0 | 456 | 0 | OK | 0 | 456 | 0 |  | 456 | 0 | 457 | 1 |  | 0 | 456 | -1 | 0 |  | 0 | 0 |  | 456 | 0 | 400 | -56 | -56 | IN Finishing
|  | GREEN | KURTA | 504 | 504 | 0 | 504 | 0 | OK | 504 | 0 | 504 | 0 | OK | 0 | 504 | 0 |  | 504 | 0 | 501 | -3 | Sonu | 0 | 501 | 0 | 504 | 0 | 504 | 0 |  | 504 | 0 | 388 | -116 | -116 | IN Finishing | 2026-03-02
|  |  | BOTTOM |  | 504 | 0 | 492 | -12 | ON DIE | 0 | 0 | 0 | 0 | OK | 0 |  | 0 |  | 492 | 0 | 491 | -1 |  | 0 | 491 | 0 | 0 | 0 | 0 | 0 |  | 504 | 0 | 388 | -104 | -116 | IN Finishing | IN
|  |  | DUPATTA |  | 504 | 0 | 504 | 0 | ON EMB | 504 | 0 | 504 | 0 | OK | 0 |  | -504 |  | 504 | 0 | 383 | -121 | cutting pending | 0 | 383 | 0 | 0 | 0 | 0 | 0 |  | 504 | 0 | 388 | -116 | -116 | 121 duppate pending | 2026-03-08 | 2026-03-09 | urgent
11 | YDPL-3450 | GREEN | KURTA | 696 | 696 | 0 | 696 | 0 | OK | 696 | 0 | 300 | -396 | 2026-03-06 | 0 |  | -300 |  |  | 0 | 0 | -696 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | FRONT YOKE EMB OUTSIDE & PATCH CUTTING | 2026-03-11 | 2026-03-15 | most utrgenty
|  |  | BOTTOM |  | 696 | 0 | 696 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 |  | 0 |  | 696 | 0 | 0 | -696 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 346 | 0 | 0 | -696 | -346 | WIP
|  |  | DUPATTA |  | 696 | 0 | 100 | -596 | IN | 0 | 0 | 0 | 0 | OK | 0 |  | 0 |  |  | 0 | 0 | -100 |  | 0 | 100 | -596 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | WASHING PROCESS FABRIC 596PCS | 2026-03-06
|  | PEACH | KURTA | 700 | 700 | 0 | 700 | 0 | OK | 700 | 0 | 300 | -400 | 2026-03-06 | 0 |  | -300 |  |  | 0 | 0 | -700 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | FRONT YOKE EMB OUTSIDE | 2026-03-11
|  |  | BOTTOM |  | 700 | 0 | 700 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 |  | 0 |  | 700 | 0 | 0 | -700 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 369 | 0 | 0 | -700 | -369 | WIP
|  |  | DUPATTA |  | 700 | 0 | 700 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 |  | 0 |  | 700 | 0 | 0 | -700 |  | 0 | 700 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -700 | 0 | WIP
12 | ADPL-3378 | BLUE | KURTA | 264 | 264 | 0 | 264 | 0 |  | 264 | 0 | 264 | 0 | OK | 0 | 264 | 0 |  | 264 | 0 | 259 | -5 | SONU | 0 | 259 | 0 | 0 | 0 | 0 | 0 |  | 259 | 0 | 232 | -32 | -27 | IN Finishing | 2026-03-07 |  | 2026-03-06
|  |  | BOTTOM |  | 264 | 0 | 264 | 0 |  | 0 | 0 | 0 | 0 | OK | 0 |  | 0 |  | 264 | 0 | 253 | -11 | SONU | 0 | 253 | 0 | 0 | 0 | 0 | 0 |  | 253 | 0 | 232 | -32 | -21 | IN Finishing | IN
|  |  | DUPATTA |  | 264 | 0 | 264 | 0 | ON EMB | 260 | 0 | 0 | -260 | OK | 0 |  | 0 |  | 264 | 0 | 258 | -6 | CUTTING PENDING | 0 | 258 | 0 | 0 | 0 | 0 | 0 |  | 258 | 0 | 232 | -32 | -26 | IN Finishing
13 | ADPL-3426R1 | BLUE | KURTA | 260 | 260 | 0 | 260 | 0 |  | 260 | 0 | 260 | 0 | OK | 0 |  | -260 |  |  | 0 | 257 | -3 | kashIf | 0 | 257 | 0 | 257 | 19 | 257 | 0 |  | 238 | 0 | 168 | 168 | -70 | IN Finishing | 2026-03-09
|  |  | BOTTOM |  | 260 | 0 | 260 | 0 |  | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  | 260 | 0 | 260 | 0 |  | 0 | 260 | 0 | 0 | 0 | 0 | 0 |  | 238 | 0 | 168 | -92 | -70 | IN FINISHING
|  |  | DUPATTA |  | 260 | 0 | 260 | 0 |  | 260 | 0 | 260 | 0 | OK | 0 | 0 | -260 |  | 260 | 0 | 260 | 0 |  | 0 | 260 | 0 | 0 | 0 | 0 | 0 |  | 238 | 0 | 168 | -92 | -70 | IN FINISHING
|  | YELLOW | KURTA | 260 | 260 | 0 | 260 | 0 |  | 260 | 0 | 260 | 0 | OK | 0 | 260 | 0 |  |  | 0 | 260 | 0 |  | 0 | 202 | -58 | 260 |  | 202+57 | #VALUE! |  | 202 | 0 | 120 | 120 | -82 | IN FINISHING | 2026-03-09
|  |  | BOTTOM |  | 260 | 0 | 260 | 0 |  | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  | 260 | 0 | 260 | 0 |  | 0 | 257 | -3 | 0 | 0 | 0 | 0 |  | 202 | 0 | 120 | -140 | -82 | IN FINISHING
|  |  | DUPATTA |  | 260 | 0 | 260 | 0 |  | 260 | 0 | 260 | 0 | OK | 0 | 260 | 0 |  | 260 | 0 | 260 | 0 |  | 0 | 260 | 0 | 0 | 0 | 0 | 0 |  | 202 | 0 | 120 | -140 | -82 | IN FINISHING
14 | ADPL-3517 | PINK | KURTA | 640 | 640 | 0 | 640 | 0 |  | 640 | 0 | 640 | 0 | CUTTING SIDE PENDING | 0 | 631 | -9 |  | 640 | 0 | 630 | -10 | SONU | 0 | 630 | 0 | 630 |  | 630 | 0 |  | 200 | 0 | 168 | -472 | -32 | IN FINISHING & ADDAWORK | 2026-03-10
|  |  | BOTTOM |  | 640 | 0 | 640 | 0 |  | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  | 640 | 0 | 640 | 0 |  | 0 | 636 | -4 | 0 | 0 | 0 | 0 |  | 200 | 0 | 168 | -472 | -32 | IN FINISHING
|  |  | DUPATTA |  | 640 | 0 | 640 | 0 |  | 640 | 0 | 640 | 0 | OK | 0 | 640 | 0 |  | 640 | 0 | 640 | 0 | CUTTING PENDING | 0 | 636 | -4 | 0 | 0 | 0 | 0 |  | 200 | 0 | 168 | -472 | -32 | IN FINISHING
|  | BLUE | KURTA | 636 | 636 | 0 | 636 | 0 |  | 636 | 0 | 636 | 0 | OK | 0 | 636 | 0 |  | 636 | 0 | 621 | -15 | SONU | 0 | 621 | 0 | 621 |  | 621 | 0 |  | 400 | 0 | 288 | -348 | -112 | IN FINISHING & ADDAWORK | 2026-03-10
|  |  | BOTTOM |  | 636 | 0 | 636 | 0 |  | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  | 636 | 0 | 636 | 0 |  | 0 | 636 | 0 | 0 | 0 | 0 | 0 |  | 400 | 0 | 288 | -348 | -112 | IN FINISHING
|  |  | DUPATTA |  | 636 | 0 | 636 | 0 |  | 636 | 0 | 636 | 0 | OK | 0 | 636 | 0 |  | 636 | 0 | 636 | 0 | OK | 0 | 656 | 20 | 0 | 0 | 0 | 0 |  | 400 | 0 | 288 | -348 | -112 | IN FINISHING
15 | ADPL-3506 | PINK | KURTA | 400 | 400 | 0 | 400 | 0 |  | 400 | 0 | 397 | -3 | 2026-03-01 | 0 | 397 | 0 |  | 397 | 0 | 398 | -2 | KASHIF | 0 | 398 | 0 | 0 | 0 | 0 | 0 |  | 398 | 0 | 398 | 1 | 0 | Closed by 26/02 | CLosed
|  |  | BOTTOM |  | 400 | 0 | 400 | 0 |  | 0 | 0 | 0 | 0 | OK | 0 |  | 0 |  | 400 | 0 | 400 | 0 | OK | 0 | 400 | 0 | 0 | 0 | 0 | 0 |  | 398 | 0 | 398 | -2 | 0 | Finishing
|  |  | DUPATTA |  | 400 | 0 | 400 | 0 |  | 0 | 0 | 0 | 0 | OK | 0 |  | 0 |  | 400 | 0 | 400 | 0 | OK | 0 | 400 | 0 | 0 | 0 | 0 | 0 |  | 398 | 0 | 398 | -2 | 0 | Finishing
|  | BROWN | KURTA | 400 | 400 | 0 | 400 | 0 |  | 400 | 0 | 397 | -3 | 2026-03-01 | 0 | 397 | 0 |  | 397 | 0 | 394 | -6 | KASHIF | 0 | 394 | 0 | 0 | 0 | 0 | 0 |  | 394 | 0 | 394 | -3 | 0 | Finishing
|  |  | BOTTOM |  | 400 | 0 | 400 | 0 |  | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  | 400 | 0 | 400 | 0 | OK | 0 | 400 | 0 | 0 | 0 | 0 | 0 |  | 394 | 0 | 394 | -6 | 0 | Finishing
|  |  | DUPATTA |  | 400 | 0 | 400 | 0 |  | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  | 400 | 0 | 400 | 0 | OK | 0 | 400 | 0 | 0 | 0 | 0 | 0 |  | 394 | 0 | 394 | -6 | 0 | Finishing
16 | ADPL-3318 | BROWN | SHIRT | 1000 | 1000 | 0 | 1000 | 0 |  | 1000 | 0 | 1058 | 58 | 2026-02-27 | 0 | 0 | -1058 |  | 1000 | 0 | 1000 | 0 | OK | 0 | 372 | -628 | 1000 | 0 | 660 | -340 | PATCH | 660 | 0 | 600 | -400 | -60 | IN FINISHING | 2026-03-07
|  |  | BOTTOM |  | 1000 | 0 | 1000 | 0 |  | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  | 1000 | 0 | 1000 | 0 | OK | 0 | 1000 | 0 | 0 | 0 | 0 | 0 |  | 660 | 0 | 600 | -400 | -60 | IN FINISHING
17 | 3523 | BROWN | SHIRT | 1200 | 1200 | 0 | 1200 | 0 |  | 1200 | 0 | 1194 | -6 | 2026-03-02 | 0 | 1194 | 0 |  |  | 0 | 1204 | 4 | OK | 0 | 900 | -304 | 1204 | 0 | 900 | -304 | BUTTON | 1100 | 0 | 1088 | 1088 | -12 | IN FINISHING & 35 PATCH PENDING | 2026-03-10
|  |  | BOTTOM |  | 1200 | 0 | 1200 | 0 |  | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  |  | 0 | 1204 | 4 | OK | 0 | 996 | -208 | 0 | 0 | 0 | 0 |  | 1100 | 0 | 1088 | 1088 | -12 | IN FINISHING
18 | ADPL-3471R1 | CREAM | KURTA | 240 | 240 | 0 | 240 | 0 |  | 240 | 0 | 240 | 0 | OK | 0 | 0 | -240 |  |  | 0 | 0 | -240 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | EMB & PINTUCKS | 2026-03-15 | 11/03 pin
|  |  | BOTTOM |  | 240 | 0 | 240 | 0 |  | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  |  | 0 | 240 | 0 |  | 0 | 240 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IN WIP
|  |  | DUPATTA |  | 240 | 0 | 240 | 0 |  | 240 | 0 | 0 | -240 | 2026-02-27 | 0 | 0 | 0 |  |  | 0 | 0 | -240 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | EMB OUTSIDE | 2026-02-27 | 2026-03-06
|  | PINK | KURTA | 276 | 276 | 0 | 276 | 0 |  | 276 | 0 | 276 | 0 | OK | 0 | 0 | -276 |  |  | 0 | 0 | -276 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | EMB OUTSIDE 24/02 | 2026-02-25
|  |  | BOTTOM |  | 276 | 0 | 276 | 0 |  | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  |  | 0 | 276 | 0 |  | 0 | 276 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IN WIP
|  |  | DUPATTA |  | 276 | 0 | 276 | 0 |  | 276 | 0 | 0 | -276 | 2026-02-27 | 0 | 0 | 0 |  |  | 0 | 0 | -276 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | EMB OUTSIDE | 2026-02-27 | 2026-03-06
19 | ADPL-3430R1 | YELLOW | KURTA | 400 | 400 | 0 | 400 | 0 | OK | 400 | 0 | 400 | 0 | OK | 0 | 400 | 0 |  |  | 0 | 0 | -400 |  | 0 | 0 | 0 | 400 |  | 262 | -138 |  | 0 | 0 | 0 | 0 | 0 | Addawork & HAND CUTTING | 2026-03-12
|  |  | BOTTOM |  | 400 | 0 | 400 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  |  | 0 | 399 | -1 |  | 0 | 399 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | WIP
|  |  | DUPATTA |  | 400 | 0 | 400 | 0 | OK | 400 | 0 | 400 | 0 | OK | 0 | 400 | 0 |  |  | 0 | 0 | -400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IN STTICHING | 2026-02-28
|  | pink | KURTA | 400 | 400 | 0 | 400 | 0 | OK | 400 | 0 | 400 | 0 | OK | 0 | 400 | 0 |  |  | 0 | 0 | -400 |  | 0 | 0 | 0 | 404 |  | 404 | 0 |  | 0 | 0 | 0 | 0 | 0 | Addawork & HAND CUTTING
|  |  | BOTTOM |  | 400 | 0 | 400 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  |  | 0 | 0 | -400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | WIP
|  |  | DUPATTA |  | 400 | 0 | 400 | 0 | OK | 400 | 0 | 400 | 0 | 2026-02-27 | 0 | 0 | -400 |  |  | 0 | 0 | -400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IN STTICHING | 2026-02-28
|  | PURPLE | KURTA | 396 | 396 | 0 | 396 | 0 | OK | 396 | 0 | 400 | 4 | OK | 0 | 400 | 0 |  |  | 0 | 0 | -396 |  | 0 | 0 | 0 | 400 |  | 200 | -200 |  | 0 | 0 | 0 | 0 | 0 | Addawork & HAND CUTTING
|  |  | BOTTOM |  | 396 | 0 | 396 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 |  |  | 0 | 396 | 0 |  | 0 | 396 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IN WIP
|  |  | DUPATTA |  | 396 | 0 | 396 | 0 | OK | 396 | 0 | 396 | 0 | OK | 0 | 396 | 0 |  |  | 0 | 0 | -396 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IN STTICHING | 2026-02-28
20 | ADPL-3543 | BLUE | KURTA | 348 | 348 | 0 | 348 | 0 | OK | 348 | 0 | 348 | 0 | OK | 0 | 348 | 0 | ON CUTTING |  | 0 | 0 | -348 | kashIf | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IN STTICHING | 2026-03-10
|  |  | BOTTOM |  | 348 | 0 | 348 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 348 | 348 |  |  | 0 | 0 | -348 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IN STTICHING
|  | MUSTARD | KURTA | 328 | 328 | 0 | 328 | 0 | OK | 328 | 0 | 328 | 0 | OK | 0 | 328 | 0 |  |  | 0 | 0 | -328 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IN STTICHING
|  |  | BOTTOM |  | 328 | 0 | 328 | 0 | OK | 0 | 0 | 0 | 0 | OK | 0 | 328 | 328 | ON CUTTING |  | 0 |  | -328 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IN STTICHING
21 | ADPL-3432R1 | GREEN | KURTA | 896 | 896 | 0 | 896 | 0 | OK | 896 | 0 | 896 | 0 | OK | 0 | 896 | 0 |  | 896 | 0 | 0 | -896 | kashIf | 0 | 0 | 0 | 202 | 0 | 0 | -202 |  | 0 | 0 | 0 | -896 | 0 | Sttiching | 2026-03-15
|  |  | BOTTOM |  | 896 | 0 | 896 | 0 | OK | 896 | 0 | 896 | 0 | OK | 0 | 896 | 0 |  | 896 | 0 | 0 | -896 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -896 | 0 | OUTSIDE Sttiching
|  |  | DUPATTA |  | 896 | 0 | 896 | 0 | OK | 896 | 0 | 896 | 0 | OK | 0 | 896 | 0 | ON CUTTING |  | 0 | 0 | -896 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IN STTICHING | 2026-03-05
|  | RUST | KURTA | 900 | 900 | 0 | 900 | 0 | OK | 900 | 0 | 900 | 0 | OK | 0 | 900 | 0 |  | 900 | 0 | 0 | -900 | kashIf | 0 | 0 | 0 | 325 | 0 | 0 | -325 |  | 0 | 0 | 0 | -900 | 0 | Sttiching
|  |  | BOTTOM |  | 900 | 0 | 900 | 0 | OK | 900 | 0 | 900 | 0 | OK | 0 | 900 | 0 |  | 900 | 0 | 0 | -900 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -900 | 0 | OUTSIDE Sttiching
|  |  | DUPATTA |  | 900 | 0 | 900 | 0 | OK | 900 | 0 | 900 | 0 | OK | 0 | 900 | 0 | ON CUTTING |  | 0 | 0 | -900 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IN STTICHING
22 | WM1006 | WINE | KURTA | 200 | 200 | [26 empty] | 184 | 0 | 0 | 0 | -184
|  |  | BOTTTOM |  | 200 | [26 empty] | 184 | 0 | 0 | 0 | -184
|  |  | DUPATTA |  | 200 | [26 empty] | 184 | 0 | 0 | 0 | -184
23 | WM1008 | BLUE | KURTA | 200 | 200 | [26 empty] | 190 | 0 | 120 | 120 | -70 |  | 2026-03-07
|  |  | BOTTOM |  | 200 | [26 empty] | 190 | 0 | 120 | 120 | -70
|  |  | DUPATTA |  | 200 | [26 empty] | 143 | 0 | 120 | 120 | -23
24 | WM1015 | GREEN | TOP | 200 | 200 | [26 empty] | 178 | 0 | 135 | 135 | -43 |  | 2026-03-07
|  |  | BOTTOM |  | 200 | [26 empty] | 178 | 0 | 135 | 135 | -43
25 | WM1009 | TEAL BLUE | KURTA | 200 | 200 | [26 empty] | 194 | 0 | 0 | 0 | -194 | Finishing Date | 2026-03-07 | 2026-03-08
|  |  | BOTTOM |  | 200 | [26 empty] | 194 | 0 | 0 | 0 | -194

## 1 - 10 March
|  |  |  | Dinesh | Dinesh |  | MIYARAM | MIYARAM | NO EDIT | MIYARAM | NIRBHAY | NIRBHAY | NIRBHAY | NO EDIT | NIRBHAY | MIYARAM | MIYARAM | NO EDIT | MIYARAM JI | MIYARAM | ISTYAAR | ISTYAAR | NO EDIT | ISTYAAR | Rajan | Rajan | NO EDIT | GAGAN JI | GAGAN | GAGAN | NO EDIT | GAGAN | Rajan | SHIV KUMAR | SHIV KUMAR | NO EDIT |  | Dinesh
S NO. | STYLE NO. | COLOUR | ITEM | ORDER QTY | ITEM WISE QTY | Start Date | TODAY CUTING QTY | TOTAL QTY | BALANCE QTY | CUTTING REMARK | ISSUE EMB | TODAY INHOUSE EMB QTY | TOTAL QTY | BALANCE QTY | EMB REMARK | TODAY RE CUTTING EMB | TOTAL RECUTTING | BALANCE EMB RECUTTING | REMARK RECUTTING | Issue Stiching | TODAY STITCHING QTY | TOTAL QTY | BALANCE QTY | REMARK STITCHING | WIP TODAY QTY | TOTAL QTY | BALANCE QTY | ISSUE ADDA WORK | TODAY ADDA QTY | TOTAL QTY | BALANCE QTY | REMARK ADDA WORK | ISSUE FINISHING QTY | TODAY FINISHING QTY | PACK TOTAL QTY | CUTTING TO FINISHING BALANCE QTY | ISSUE TO FINISHING BALANCE | REMARK | Timeline | Exceeded Time | Final Time Line | Production Days
| Total - |  |  | 19500 | 66326 | 2026-02-04 | 0 | 65606 | -720 | 21720 | 5980 | 5360 | 8746 |  |  | 4922 | 3978 | 0 | 0 | 23018 | 0 | 5558 | 0 |  | 0 | 0 | 0 | 506 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 2026-03-09 | 33
1 | YDPL-3481 | Green | KURTA | 500 | 500 |  |  | 464 | -36 | 464 |  | 464 | 0 | OK |  | 464 | 464 |  |  | 464 |  |  |  | kashIf | [5 empty] | SLeeves Adda Front checking | [8 empty] | 2026-03-15 |  |  | 0
|  |  | BOTTOM |  | 500 |  |  | 464 | -36 | [9 empty] | PAN BOR PEND | [10 empty] | Inhouse | [11 empty] | 0
|  |  | DUPATTA |  | 500 |  |  | 464 | -36 | ON EMB |  |  |  | OK | [27 empty] | 0
|  | PEACH | KURTA | 500 | 500 |  |  | 460 | -40 | 460 | 460 | 460 | 0 |  |  | 460 | 460 |  |  | 460 |  |  |  | kashIf | [17 empty] | 0
|  |  | BOTTOM |  | 500 |  |  | 460 | -40 | [9 empty] | PANT BOR PEND | [10 empty] | Inhouse | [11 empty] | 0
|  |  | DUPATTA |  | 500 |  |  | 460 | -40 | RE DIE |  | 460 |  | 2026-03-03 | [15 empty] | Duppata on Redye | [11 empty] | 0
2 | ADPL-3244 | BROWN | SHIRT | 1500 | 1500 |  |  | 1504 | 4 |  |  | 1500 |  | 2026-03-09 | [5 empty] | 1504 |  | 1500 |  | kashIf | [13 empty] | final | 2026-03-10 |  |  | 0
|  |  | PANT |  | 1500 |  |  | 1504 | 4 | [10 empty] | 1504 |  | 1500 |  | kashIf | [13 empty] | emb patch | 2026-03-07 |  |  | 0
3 | YDPL-3489 | YELLOW | KURTA | 600 | 600 |  |  | 600 | 0 | 600 |  | 600 |  | 2026-03-09 | [23 empty] | emb | 2026-03-10 |  |  | 0
|  |  | BOTTOM |  | 600 |  |  | 600 | 0 | ON DYE | [31 empty] | 0
|  |  | DUPATTA |  | 600 |  |  | 600 | 0 | [28 empty] | final production | 2026-03-18 |  |  | 0
|  | PINK | KURTA | 600 | 600 |  |  | 600 | 0 | 600 |  | 600 |  | 2026-03-09 | [27 empty] | 0
|  |  | BOTTOM |  | 600 |  |  | 600 | 0 | ON DYE | [31 empty] | 0
|  |  | DUPATTA |  | 600 |  |  | 600 | 0 | [32 empty] | 0
4 | YDPL-3498 | BLUE | KURTA | 800 | 928 |  |  | 928 | 0 | 928 |  |  |  | 2026-03-03 | [23 empty] | emb | 2026-03-10 |  |  | 0
|  |  | BOTTOM |  | 928 |  |  | 928 | 0 | [32 empty] | 0
|  |  | DUPATTA |  | 928 |  |  | 928 | 0 | [28 empty] | final | 2026-03-18 |  |  | 0
|  | MAROON | KURTA | 800 | 800 |  |  | 784 | -16 | 784 |  |  |  | 2026-03-03 | [27 empty] | 0
|  |  | BOTTOM |  | 800 |  |  | 784 | -16 | [32 empty] | 0
|  |  | DUPATTA |  | 800 |  |  | 784 | -16 | [32 empty] | 0
5 | YDPL-3507 | BLUE | KURTA | 600 | 600 |  |  | 612 | 12 | 612 |  |  | 612 | 2026-03-06 | [23 empty] | emb | 2026-03-08 |  |  | 0
|  |  | BOTTOM |  | 600 |  |  | 612 | 12 | [28 empty] | Final | 2026-03-18 |  |  | 0
[9 empty] | 0 | [28 empty] | Final |  |  |  | 0
|  | GREEN | KURTA | 600 | 616 |  |  | 616 | 0 | 616 |  |  | 616 | 2026-03-03 | [27 empty] | 0
|  |  | BOTTOM |  | 616 |  |  | 616 | 0 | [32 empty] | 0
[9 empty] | 0 | [32 empty] | 0
6 | YDPL-3503 | RED | KURTA | 600 |  |  |  |  | 0 |  | TO BE PRINTED | [26 empty] | urgent cutting | 2026-03-07 |  |  | 0
|  |  | BOTTOM | [5 empty] | 0 | [28 empty] | print |  |  |  | 0
|  |  | DUPATTA | [5 empty] | 0 | [28 empty] | final | 2026-03-15 |  |  | 0
|  | BLUE | KURTA | 600 |  |  |  |  | 0 |  | SLEEVES ON WASHING | [30 empty] | 0
|  |  | BOTTOM | [5 empty] | 0 | [32 empty] | 0
|  |  | DUPATTA | [5 empty] | 0 | [32 empty] | 0
7 | ADPL-3470 R2 | OFF-WHITE | KURTA | 400 | 364 |  |  | 364 | 0 | 364 |  |  |  | OK |  | 364 | 364 |  |  | 364 | [17 empty] | final | 2026-03-10 |  |  | 0
|  |  | BOTTOM |  | 364 |  |  | 364 | 0 |  | OK | [30 empty] | 0
|  |  | DUPATTA |  | 364 |  |  | 364 | 0 | [28 empty] | duppttaa | 2026-03-07 |  |  | 0
|  | GREEN | KURTA | 400 | 450 |  |  | 450 | 0 | 450 | PENDING 2 SIZE |  |  | 2026-03-10 | [5 empty] | 450 | [21 empty] | 0
|  |  | BOTTOM |  | 450 |  |  | 450 | 0 | [6 empty] | 450 | 450 | [24 empty] | 0
|  |  | DUPATTA |  | 450 |  |  | 450 | 0 | [32 empty] | 0
8 | YDPL-3482 | YELLOW | KURTA | 500 | 488 |  |  | 488 | 0 | 488 | 488 | 0 |  | 2026-03-03 |  | 488 | 488 |  |  | 488 | [17 empty] | emb | 2026-03-10 |  |  | 0
|  |  | BOTTOM |  | 488 |  |  | 488 | 0 | [32 empty] | 0
|  |  | DUPATTA |  | 488 |  |  | 488 | 0 | [10 empty] | 488 | [21 empty] | 0
|  | PINK | KURTA | 500 | 476 |  |  | 476 | 0 | 476 | 476 | 0 |  | 2026-03-03 |  | 476 | 476 |  |  | 476 | [17 empty] | final | 2026-03-20 |  |  | 0
|  |  | BOTTOM |  | 476 |  |  | 476 | 0 | [32 empty] | 0
|  |  | DUPATTA |  | 476 |  |  | 476 | 0 | [10 empty] | 476 | [21 empty] | 0
|  | GREY BLUE | KURTA | 500 | 476 |  |  | 476 | 0 |  | 476 |  |  |  |  | 476 | 476 |  |  | 476 | [21 empty] | 0
|  |  | BOTTOM |  | 476 |  |  | 476 | 0 | [28 empty] | pant pending | 2026-03-07 |  |  | 0
|  |  | DUPPTTA |  | 476 |  |  | 476 | 0 | [10 empty] | 476 | [21 empty] | 0
9 | ADPL-3443 R1 | PINK | KURTA | 400 | 400 |  |  | 400 | 0 | 400 | 400 | 0 |  | OK |  | 400 | [5 empty] | 297 | [5 empty] | 297 | [9 empty] | Final | 2026-03-10 |  |  | 0
|  |  | BOTTOM |  | 400 |  |  | 400 | 0 | [5 empty] | ISSUED |  | 400 |  |  | 400 | [21 empty] | 0
|  |  | DUPPTTA |  | 400 |  |  | 400 | 0 | 400 |  |  |  | 2026-03-03 | [27 empty] | 0
|  | ICE BLUE | KURTA | 400 | 400 |  |  | 400 | 0 | 400 | 400 | 0 |  | OK | ISSUED | 400 | 400 |  |  | 400 |  | 209 | [5 empty] | 209 | [13 empty] | 0
|  |  | BOTTOM |  | 400 |  |  | 400 | 0 | [32 empty] | 0
|  |  | DUPPTTA |  | 400 |  |  | 400 | 0 | 400 |  |  |  | 2026-03-03 | [27 empty] | 0
10 | ADPL-3423 R1 | BLUE | KURTA | 700 | 700 |  |  | 700 | 0 | 700 | 700 | 0 |  | OK |  | RE CUTTING | [21 empty] | final | 2026-03-15 |  |  | 0
|  |  | BOTTOM |  | 700 |  |  | 700 | 0 | 700 | 700 |  |  | OK | [7 empty] | 700 | [19 empty] | 0
|  |  | DUPPTTA |  | 700 |  |  | 700 | 0 | 700 |  |  |  | 2026-03-03 | [27 empty] | 0
|  | RED | KURTA | 700 | 704 |  |  | 704 | 0 | 704 | 704 | 0 |  | OK |  | RE CUTTING | [25 empty] | 0
|  |  | BOTTOM |  | 704 |  |  | 704 | 0 | 704 | 704 | 0 |  | OK | [7 empty] | 704 | [19 empty] | 0
|  |  | DUPPTTA |  | 704 |  |  | 704 | 0 | 704 |  |  |  | 2026-03-03 | [27 empty] | 0
11 | AYKAA3388 R1 | BLUE | KURTA |  | 472 |  |  | 472 | 0 | 472 | 472 | 0 |  | OK |  | 472 |  |  |  | 472 |  | 448 | [15 empty] | handwork | 2026-03-07 |  |  | 0
|  |  | BOTTOM |  | 472 |  |  | 472 | 0 | [10 empty] | 472 | [21 empty] | 0
|  |  | DUPPTTA |  | 472 |  |  | 472 | 0 | 472 |  |  | 472 | 2026-03-01 |  | 472 |  |  |  | 472 | [21 empty] | 0
12 | ADPL-3391 R1 | PEACH | KURTA |  | 500 |  |  | 500 | 0 | 500 |  |  | 500 | 2026-03-06 |  | IN | [25 empty] | 0
|  |  | BOTTOM |  | 500 |  |  | 500 | 0 | [28 empty] | final | 2026-03-15 |  |  | 0
|  |  | DUPPTTA |  | 500 |  |  | 500 | 0 | [6 empty] | IN | [25 empty] | 0
13 | ADPL-3103 | PEACH | KURTA |  | 260 |  |  | 260 | 0 | 260 |  |  | 260 | 2026-03-03 | [23 empty] | emb | 2026-03-10 |  |  | 0
|  |  | BOTTOM | [5 empty] | 0 | ON DYE | [19 empty] | ON DYE | [7 empty] | final | 2026-03-18 |  |  | 0
|  |  | DUPPTTA |  | 260 |  |  |  | -260 | ON EMB | [31 empty] | 0
14 | ADPL-3486 | BLUE | KURTA |  | 600 |  |  | 600 | 0 | 600 |  |  | 600 | 2026-03-03 | [23 empty] | emb | 2026-03-10 |  |  | 0
|  |  | BOTTOM |  | 600 |  |  | 600 | 0 | [10 empty] | 600 | [9 empty] | BOTTOM STITCHING OUTSIDE I | [7 empty] | final | 20/03\ |  |  | 0
|  |  | DUPPTTA |  | 600 |  |  | 600 | 0 | [10 empty] | 600 | [9 empty] | IN HOUSE STITCH | [11 empty] | 0
|  | MUSTARD | KURTA |  | 600 |  |  | 600 | 0 | 600 |  |  | 600 | 2026-03-03 | [27 empty] | 0
|  |  | BOTTOM |  | 600 |  |  | 600 | 0 | [10 empty] | 600 | [9 empty] | BOTTOM STITCHING OUTSIDE | [11 empty] | 0
|  |  | DUPPTTA |  | 600 |  |  | 600 | 0 | [10 empty] | 600 | [9 empty] | INHOUSE STITCHING | [11 empty] | 0
15 | WM1013 | PURPLE | KURTA |  | 200 |  |  | 200 | 0 | 200 |  | 200 | 0 | OK | [5 empty] | 200 | [17 empty] | final | 2026-03-07 |  |  | 0
|  |  | BOTTOM |  | 200 |  |  | 200 | 0 | [10 empty] | 200 | [21 empty] | 0
|  |  | DUPPTTA |  | 200 |  |  | 200 | 0 | [10 empty] | 200 | [21 empty] | 0
16 | WM1018 | BLUE | SHIRT |  | 200 |  |  | 200 | 0 | [10 empty] | 200 | [17 empty] | final | 2026-03-08 |  |  | 0
|  |  | PANT |  | 200 |  |  | 200 | 0 | [10 empty] | 200 | [21 empty] | 0
17 | WM1002 | MUSTARD | KURTA |  | 180 |  |  | 180 | 0 |  |  |  |  | OK | [5 empty] | 180 | [17 empty] | FINAL | 2026-03-09 |  |  | 0
|  |  | BOTTOM |  | 180 |  |  | 180 | 0 | [10 empty] | 180 | [21 empty] | 0
|  |  | DUPPTTA |  | 180 |  |  | 180 | 0 | [9 empty] | IN HOUSE | [22 empty] | 0
18 | WM1012 | PINK | KURTA |  | 200 |  |  | 200 | 0 |  |  | 200 | 0 | OK | [23 empty] | FINAL | 2026-03-14 |  |  | 0
|  |  | BOTTOM |  | 200 |  |  | 200 | 0 | [32 empty] | 0
|  |  | DUPPTTA |  | 200 |  |  | 200 | 0 | [32 empty] | 0
19 | WM1014 | PURPLE | KURTA |  | 200 |  |  | 200 | 0 | [9 empty] | CHECKING |  |  | 200 |  | 200 | [13 empty] | final | 2026-03-12 |  |  | 0
|  |  | BOTTOM |  | 200 |  |  | 200 | 0 | [10 empty] | 200 | [21 empty] | 0
|  |  | DUPPTTA |  | 200 |  |  | 200 | 0 | [10 empty] | 200 | [21 empty] | 0
20 | WM1017 |  | SHIRT | [5 empty] | 0 | [28 empty] | final | 2026-03-16 |  |  | 0
|  |  | PANT | [5 empty] | 0 | [32 empty] | 0
21 | ADPL3300R2 | PEACH | TOP |  | 144 |  |  | 144 | 0 | 144 |  |  | 144 | [24 empty] | emb | 2026-03-09 |  |  | 0
|  |  | BOTTOM |  | 144 |  |  | 144 | 0 | [28 empty] | final | 2026-03-20 |  |  | 0
|  | PURPLE | TOP |  | 208 |  |  | 208 | 0 | 208 |  |  | 208 | [28 empty] | 0
|  |  | BOTTOM |  | 208 |  |  | 208 | 0 | [32 empty] | 0
22 | ADPL-3328R6 | BROWN | TOP |  | 808 |  |  | 808 | 0 | 808 |  |  | 808 | 2026-03-10 | [23 empty] | emb | 2026-03-11 |  |  | 0
|  |  | INNER |  | 808 |  |  | 808 | 0 | [28 empty] | final | 2026-03-18 |  |  | 0
|  |  | BOTTOM |  | 808 |  |  | 808 | 0 | [10 empty] | 808 | [21 empty] | 0
23 | ADPL-3233 R13 | BROWN | TOP |  | 1000 |  |  | 1000 | 0 | 1000 |  |  | 1000 | 2026-03-03 | [23 empty] | final | 2026-03-09 |  |  | 0
|  |  | BOTTOM |  | 1000 |  |  | 1000 | 0 | [32 empty] | 0
0
24 | ADPL-3480 | BROWN | TOP |  | 1404 |  |  | 1404 | 0 | 1404 |  |  | 1404 | 2026-03-09 | [5 empty] | 1404 | [17 empty] | emb | 2026-03-09 |  |  | 0
|  |  | BOTTOM |  | 1404 |  |  | 1404 | 0 | [10 empty] | 1404 | [17 empty] | final | 2026-03-15 |  |  | 0
0
25 | YDPL-3485 | PINK | KURTA | 500 | 500 |  |  | 424 | -76 | 424 |  | 424 |  | 2026-03-10 | [27 empty] | 0
|  |  | BOTTOM |  | 500 |  |  | 424 | -76 | [32 empty] | 0
|  |  | DUPATTA |  | 500 |  |  | 424 | -76 | [32 empty] | 0
|  | YELLOW | KURTA | 500 | 500 |  |  | 452 | -48 | 452 |  | 452 |  | 2026-03-10 | [27 empty] | 0
|  |  | BOTTOM |  | 500 |  |  | 452 | -48 | [32 empty] | 0
|  |  | DUPATTA |  | 500 |  |  | 452 | -48 | [32 empty] | 0
26 | YDPL-3490 | MAROON | KURTA | 500 | 500 |  |  | 422 | -78 |  |  |  |  | 2026-03-13 | [27 empty] | 0
|  |  | BOTTOM |  | 500 |  |  | 422 | -78 | [32 empty] | 0
|  |  | DUPATTA |  | 500 |  |  | 422 | -78 | [32 empty] | 0
|  | BLUE | KURTA | 500 | 500 |  |  | 516 | 16 |  |  |  |  | 2026-03-13 | [27 empty] | 0
|  |  | BOTTOM |  | 500 |  |  | 516 | 16 | [32 empty] | 0
|  |  | DUPATTA |  | 500 |  |  | 516 | 16 | [32 empty] | 0
27 | YDPL-3509 | BURGUNDY | KURTA | 300 | 174 |  |  | 174 | 0 | 174 |  |  | 174 | APPROVED | [27 empty] | 0
|  |  | BOTTOM |  | 174 |  |  | 174 | 0 | [32 empty] | 0
[8 empty] | 174 | 174 | [32 empty] | 0
|  | BLUE | KURTA | 300 | 168 |  |  | 168 | 0 | 168 |  |  | 168 | APPROVED | [27 empty] | 0
|  |  | BOTTOM |  | 168 |  |  | 168 | 0 | [32 empty] | 0
[8 empty] | 168 | 168 | [32 empty] | 0
28 | YDPL-3465 | BLUE | KURTA | 600 | 600 |  |  | 600 | 0 | 600 |  |  | 600 | APPROVAL | [27 empty] | 0
|  |  | BOTTOM |  | 600 |  |  | 600 | 0 | [32 empty] | 0
|  |  | DUPATTA |  | 600 |  |  | 600 | 0 | [32 empty] | 0
|  | MUSTARD | KURTA | 600 | 580 |  |  | 580 | 0 | 580 |  |  | 580 | APPROVAL | [27 empty] | 0
|  |  | BOTTOM |  | 580 |  |  | 580 | 0 |  | OK | [30 empty] | 0
|  |  | DUPATTA |  | 580 |  |  | 580 | 0 |  | OK | [30 empty] | 0
29 | #3244 R13 | Brown | Top | 800 | 800 |  |  | 800 | [11 empty] | 800 | [21 empty] | 0
|  |  | Bottom |  | 800 |  |  | 800 | [11 empty] | 800 | [21 empty] | 0
|  |  | Shirt |  | 800 |  |  | 800 | [11 empty] | 800 | [21 empty] | 0
30 | #3233 R14 | Brown | TOP | 1500 | 1500 |  |  | 1500 | [11 empty] | 1500 | [21 empty] | 0
|  |  | BOTTOM |  | 1500 |  |  | 1500 | [11 empty] | 1500 | [21 empty] | 0
31 | #3480 | Brown | TOP | 1200 | 1200 |  |  | 1200 | [10 empty] | ON CUTTING | [22 empty] | 0
|  |  | BOTTOM |  | 1200 |  |  | 1200 | [10 empty] | ON CUTTING | [22 empty] | 0
|  |  | Total - | 26238 | [37 empty] | 0

## 11 - 20 MARCH
S NO. | STYLE NO. | COLOUR | ITEM | ORDER QTY | ITEM WISE QTY | TODAY CUTING QTY | TOTAL QTY | BALANCE QTY | ISSUE EMB | TODAY INHOUSE EMB QTY | TOTAL QTY | BALANCE QTY | EMB REMARKS | Issue Sttiching | TODAY STITCHING QTY | TOTAL QTY | BALANCE QTY | WIP TODAY QTY | TOTAL QTY | BALANCE QTY | ISSUE ADDA WORK | TODAY ADDA QTY | TOTAL QTY | BALANCE QTY | ISSUE FINISHING QTY | TODAY FINISHING QTY | TOTAL QTY | BALANCE QTY | REMARK
1 | YDPL-3485 | PINK | KURTA | 600 | 600 |  | 424 | -176 | 424 |  | 424 |  | 2026-03-10
|  |  | BOTTOM |  | 600 |  | 424 | -176 |  | ON DYE
|  |  | DUPATTA |  | 600 |  | 424 | -176 |  | ON DYE
|  | YELLOW | KURTA | 600 | 600 |  | 452 | -148 | 452 |  | 452 |  | 2026-03-10
|  |  | BOTTOM |  | 600 |  | 452 | -148 |  | ON DYE
|  |  | DUPATTA |  | 600 |  | 452 | -148 |  | ON DYE
3 | YDPL-3490 | MAROON | KURTA | 600 | 600 |  | 422 | -178 |  |  |  |  | 2026-03-13
|  |  | BOTTOM |  | 600 |  | 422 | -178 |  | ON DYE
|  |  | DUPATTA |  | 600 |  | 422 | -178 |  | ON DYE
|  | BLUE | KURTA | 600 | 600 |  | 516 | -84 |  |  |  |  | 2026-03-13
|  |  | BOTTOM |  | 600 |  | 516 | -84 |  | ON DYE
|  |  | DUPATTA |  | 600 |  | 516 | -84 |  | ON DYE
4 | YDPL-3509 | BURGUNDY | KURTA | 300 | 174 |  | 174 | 0 | 174 | 2 PCS HA |  | 174 | APPROVED
|  |  | BOTTOM |  | 174 |  | 174 | 0
[7 empty] | 174 | 174
|  | BLUE | KURTA | 300 | 168 |  | 168 | 0 | 168 | 2 PCS HA |  | 168 | APPROVED
|  |  | BOTTOM |  | 168 |  | 168 | 0
[7 empty] | 168 | 168
5 | YDPL-3465 | BLUE | KURTA | 600 | 600 |  | 600 | 0 | 600 |  |  | 600 | APPROVAL
|  |  | BOTTOM |  | 600 |  | 600 | 0 |  | OK
|  |  | DUPATTA |  | 600 |  | 600 | 0 |  | OK
|  | MUSTARD | KURTA | 600 | 580 |  | 580 | 0 | 580 |  |  | 580 | APPROVAL
|  |  | BOTTOM |  | 580 |  | 580 | 0 |  | OK
|  |  | DUPATTA |  | 580 |  | 580 | 0 |  | OK
6
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30